## High Priority
HR Project Charter - 2026-27
| HR Projects | Frequency | Timelines for Institutionalization & Adoption | Action Plan | Business Impact | Success Measures | Status Update | Timelines Met /Deferred | Revised Timeline | Support Required
SNO | Employee Communication - Building Culture of Transparency, Openess and Trust
1 | HR Focus Group Session | Fortnightly | Q3-May-26 | 1. FGD calendar defined & signed off with delivery team | 1. Enhanced employee engagement 2. Building culture of openess & transparency 3. Increased productivity and reduced turnover 4. Operational & cultural insights | 1. ESAT Survey Score 2. Employee Net Promoter Score (eNPS) score 3. Employee turnover/retention%
2 | HR Skips Session | Monthly | Q3-May-26 | 1. HR Skip Session calendar defined & signed off with delivery team
3 | Leadership - Open House /Townhall Sessions | Quarterly | Q2-Mar-26 | 1. Leadership connect calendar defined and signed off with the Management
SNO | Competency & Skill Management - Employee Producvity and Efficiency
1 | Career Framework (CF)- Standardised Grades /Level & Designation | One Time Set up | Q3-Jul-26 | 1. Define Career Framework at an enterprise level for management review 2. Taking Sign off from management for the finalised Framework 3. Mapping Employees as per the Grade/Level 4. Issue Addendum Letters for the Grade/Level or incorporate in the appraisal process for tenured employees. Issueing LOI/OL/AL to tne new joiners with Grade/Level as per CF | 1. Overall consistency and governance in Organisation hierarchy 2. Increased Organizational agility - aligning employee capabilities with evolving business needs 3. Strategic succession planning for key/critical business roles 4. Talent development and Skill Gap identification 5. High Employee engagement and retention rate | 1. Increased Organizational Efficiency 2. Market Competitiveness - C&B benchmarking grades against industry standards 2. Standardised Career Progression Paths - promition cases % 3. Scalability During Orgniasation Growth 4. Enhanced Talent Retention & Attraction | i. CF draft version created ii. Leader workshop to be organised for VP & Above+ Location Heads, Business Heads (APAC, MEA, UK) for cascading and taking Leader inputs /observations
2 | Career Ladder - Structured Career Path Progression | Process Gudelines | Q3-Jul-26 | 1. Draft Performance Appraisal Policy incorporating promotion guidelines for management review 2. Draft recruitment Policy incorporating career progression guidelines for management review 3. Draft High Potential Program draft for management review 4. Leverage AAIRO for building & grouping of Skill repository at designation 5. Leverage AAIRO for baselining skill required for a specific role 6. Leverage AAIRO for skill gap analysis 7. AAIRO tool to baseline and club skills for recruiters. Resourcing Pool can be maintained across Sector /Vertical. Cross Pollination os skills maintaning trained cross skilled productive bench as per market demand & supply condition 8. Employe to be offered Career Path progression options as per skill and competence and avaialble positiones (new /backfill) 9. Effective Resourcing Management - Cross skilled talent pipeline available 10. Internal Talent pipeline, reduce the delivery time of external sourcing. Impact directly on business delivery | 1. Structured Career path progression for freshers 2. Career path progression for lateral (horizontal /vertical) 3. High employee engagement & job satisfaction level 4. Embedding Learining culture - continuous learning and skill acquisition (upskilling & cross skilling) | 1. Early Attrition% in 6-12 months 2. Employee Engagement & Satisfaction - ESAT Survey Score 4. High-Potential Talent retention 5. Succession Pipeline Strength 6. Internal Mobility Rate - promotion cases % | i. Career Ladder draft version ready ii. Leader workshop to be organised for VP & Above+ Location Heads, Business Heads (APAC, MEA, UK) for cascading and taking Leader inputs /observations
3 | Learning & Development | Policy Guidelines | Q3-Aug-26 | 1. Draft L&D Policy for management review 2. Segmented learning programs as per role 3. Identify vendors offering e-learning programs - e-learning / off shelf LMS Platform - SkillSoft, Linkedin Learning, Udemy, Coursera 4. Present Business case with CBA analysis to the management 5. Company Sponsored training /certification /EYE/C with Lock-in based reimbursement or claw-back option 6. AI-Trainer (Generates Audio from ppt slides) - tool for conducting induction trainings for new joiner - Freshers /Lateral 7. AI-Trainer - tool to be used for conducting recruiter refresher trainings - Process, Tool, Compliances and others. Building Culture of Compliance and Meritocracy 8. Training Plotter timelines for lateral hires can be reduced using AI-Trainer 9. Assessment /Quiz to have level of difficulty with baseline to pass the course 10. AI-Trainer - tool to be used for Soft skills training, behavioral training and mid-level leadership training programs 11. AAIRO tool to be used for baselining skills across grades. 12. AAIRO tool to be used for skill-gap analysis and identification of specific training program at a particular grade/level | 1. Building culture of innovation & change management 2. Improved Agility and Adaptability 4. Increased Profitability and Productivity 3. Future ready talent workforce 4. Stronger Succession Planning via internal talent pipeline | 1. Internal Mobility and Promotion Rates % 2. Employee Engagement & Satisfaction - ESAT survey results 3. Performance and Productivity Metrics 4. Reduced employee turnover % 5. Optimising l&D Department | i. Learning and Development Policy drafted ii. Meeting with e-learning vendors - Coursera, SkillSoft, Udemy lined up for this week iii. AI - Trainer tool demo scheduled for wk-1 April
4 | Performance Management Review (PMR) process | Process Gudelines | Q3-Aug-26 | 1. Draft PMR Policy for Management review 2. Draft PMR Form with WAR (Weighted average rate (% Contribution of Goals /Values /Behavior or Competencies) for management review 3. End to end PMR Pocesss digitisation on Grey HR /Keka HR to be discussed with management. Or Proposed new HRMS System - Darwinbox, PeopleStrong 4. AAIRO score inputs weightage to be added with goal sheet for final rating | 1. Improved Strategic Alignment with planned approach of goal setting linked with overall company goals with a structured review mechanism 2. Improved Organizational Agility & Innovation 3. Enhanced Productivity & Results 4. Increased Employee Engagement & Retention | 1. Goal Alignment & Achievement Rate - aligning individual goals with organizational strategy to drive profitability and productivity 2. Employee Productivity & Efficiency 3. Productivity & efficiency vis-à-vis BQM process 4. Capability Building & Development 5. Retention and Turnover Rates% | i. Performance Management Review Policy drafted
5 | Compensation & Benefits -Internal Benchmarking | Process Gudelines | Q3-Sep-26 | 1. AAIRO tool can help with Internal Salary ranges with similar profile across departments 2. Tool can be sused for defining minimum-median-maximum salary range for particular Band /Levle | 1. Pay Equity and Compliance 2. Talent Acquisition & Retention - competitive salaries that attract high-quality candidates 3. Financial Sustainability of business 4. Transparent Pay Structures | 1. Reduced Employee Turnover 2. Internal Pay Equity 3. Market Ratio (Compa-Ratio) 4. Elimination of Outliers in particular grade/ level 5. Compensation Strategy Adoption - Clear definition of market positioning ( matching the market at 50th percentile) 6. Budget Alignment - ercentage of the workforce within established pay bands
6 | Recruiter Productivity & Efficiency Enhancement | Process Gudelines | Q4-Nov-26 | 1. AI-Sentivox tool - calibration of the recruiter interviview with candidate and candidate and vice versa (Emotional Intelligence /Sentiments) 2. Recruiter Score at business vertical level, baselining score and conducting stack rank 3. BQM Analytics - recruiter with consistent low scores in a quarter to be reffered to BQM process. 4. Recruiter Calibration across Sector /Vertical 5. Creation of Standardized script for the recruiter interviews. Common interview Tool Kit and Question Bank 6. Predictive Analytics & Co-relation of Recruiter Sentivox Score vis-a-vis Recruiter Scorecard for linkages and further refinement on development needs | 1. Financial Performance - higher revenue growth and improved profitability 2. Operational Efficiency - competitive advantage and sustainable growth in dynamic markets 3. Innovation and Growth 4. Customer Satisfaction 5. Employee Engagement & Retention | 1. Revenue per Employee 2. Goal Completion (KPIs/OKRs) 3. CSAT Scores 4. Turnover Rates 5. Absenteeism/Attendance Rates | i. AI-Sentivox tool demo planned for wk-1 April-26
7 | Talent Management & Suceession Planning | Process Gudelines | Q4-Nov-26 | 1. Draft Talent Management Policy for management review 2. Identification of key roles in every department /function which has direct impact on business continuity 3. Identifying Potential successor /High Potentials for the role - creating IDP plan with structured reviews on pre-defined timelines 4. Hi Po's Risk Assessment - Potential & Performance with monthly RAG analysis 5. Leadership Assessments for future leaders for critical roles - explore assessments with leading companies - Mercer, DDI, others 6. AAIRO tool interview baseline scores at all levels with predefined frequency Monthly /Quarterly - employeees with consistent high scores can be part of the HiPo process | 1. Business continuity & risk management 2. Higher Organizational Profitability 3. Buliding Internal talent & leadership capabilities for future organisations expansion/growth 4. Leadership Pipeline Development 5. Cost reduction vis-a-vis hiring of external talent 6. Increased Agility | 1. Bench strength/Internal Talent pipeline 2. Internal Mobility Rate & Promotion Rates 3. Succession Planning Rate 4. Employee Retention Rate & Voluntary Turnover 5. Diversity and Inclusion Metrics 6. TAT for position closure | i. Talent Management & Succession planning approach note in progress
SNO | Employee Engagement - Building Culture of Performance & Innovation
1 | Rewards & Recognition Process 1. P2P (Peer 2 Peer) Awards introduction - Thank You cards 2. Long Sservice Awards 3. Spot Awards - You Made the difference /Extra Miler /Pat on the Back 4. Company Value Cards Awards - VMV Alignment 5. Optimiser or Best Idea /Innovation - US$ Saving & Process Improvement or Productivity enhancement 6. Category for Highest and consistent AARIO Scores of the year Employee Well Being 1. Health and Well Being 2. Employee Assistance Program (EAP) | Process Gudelines | Q3-Sep-26 | 1. Draft Employee Reward & Recognition Policy for management review 2. Define Reward categories, eligibility and other parameters 3. Define the R&R assessment process 4. e- Wall of fame - Darwinbox 5. R&R process digitisation - XOXO day, AdvantageClub.ai 6. Identify Vendors offering EAP programs - confidential counseling, mental health resources, and work-life support - 1to1, Your Dost and others 7. Health & Wellness programs via Mediclaim (TPA) vendor (MediAssist, MDIndia, Paramount Health, Park Mediclaim , others) - Doctor on campus, discounted tie-ups with Pharmacy, hospitals, Gym and others 7. TPA mobile App offering online facilities for Doctor consultation, 24*7 pharmacy support | 1. High employee engagement & experience quotient 2. Building employee alignment with organisation cuture - Vision, Mission and Values 3. Improved Retention and reduced turnover 4. Increased Profitability and Performance 5. Boosted Productivity and Quality 6. Higher Innovation and Agility 7. Reduced Absenteeism and Health Risks | 1. Employee Net Promoter Score (eNPS) score -Measures loyalty 2. Voluntary Turnover & Retention Rates % 3. Productivity & Performance Metrics 4. Absenteeism Rate % | i. Rewards & Recognition Policy drafted ii. R&R Process digitisation - Meeting with XOXO day vendor completed
SNO | Operational Processes Streamlining & Standardisation
1 | Process Streamling & Standardization - SOP, Manual & Playbook creation | Ongoing | Q3-Sep-26 | 1. Creation of SOP and Process Manual for - UK, US and Cananda - HR 2. Standardized Process Playbook for tools used in the processes 3. Standardisation and documentation of process workflows | 1. Process consistency and quality assurance 2. Process compliance and risk mitigation 3. Process knowledge retention and business continuity 4. Standardised and streamlined processes have no impact from current or future business state 5. Efficient training and onboarding of new resources via process standard KT | 1. Operational efficiency & productivity - measure of cycle time and operational cost reduction 2. Quality and consistency - measure of process defect % 3. Compliance and risk management - measure of internal/external audits success rates, incident rate % | 1. Code of Conduct and Ethics drafte version completed 2. Process SOP documentation is WIP
HRMS System -Consolidation at group level
1 | HR Process Digitization - Consolidate current system or evlauate new global system | On time set-up and implementation | Q3-Aug-26 | 1. Feasibility of current HRMS System - Grey HR or Keka HR for consolidation at group level 2. Evaluation of Global HRMS System - SAP - Success Factor, Bamboo HR, Oracle -Fusion, Workday 3. Evaluation of local HRMS players with an international presence - Peoplestrong, Darwinbox | 1. Improved Efficiency & Productivity 2. Data-Driven Decision Making 3. Cost Optimization & Scalability 4. Compliance & Risk Mitigation 5. Data Security 6. Enhanced HR Service Delivery | 1. Operational efficiency & productivity - measure of cycle time and operational cost reduction in HR processes 2. Employee Net Promoter Score (eNPS) 3. Higher Revenue per Employee - Increased efficiency linked to higher productivity 4. Improved Compliance Management | i. Vendor - PeopleStrong demo's organisaed for modules - Core, L&A, PMR, L&D, TM. TA and OB Modules demo scheduled from Wk1-Wk-4 April-26 ii. PeopleStrong demo planned for Finance Team Wk-3-April iii. Vendor- Darwinbox demos planned from Wk1-Wk4 April-26 iv. Vendor SAP- Success Factor demo planned for wk-1 May-26 v. Vendora Workday demo planned for wk-1 May-26 vi. Vendor Oracle - Fusion demo planned for wk-1-May-26
Employer Branding - External and Internal - Employer of Choice
1 | Employer Branding | Annual | Q4-Dec-26 | 1. Share draft plan with the Management for the GPTW Certification 2. Post Management approval, initiate the process for certification and further processing 3. VOW (Voice of Workforce) Surveys - Multiple Theme Pulse Surveys on basis of GPTW Trust Index Questinnaire format with employees department wise 4. Sharing Survey result with Department Manager and working on action plan 4. Workshop Managers for the GPTW Approach 5. Managers to cascade messaging to the diret reports and within teams 6. GPTW Awareness Session on Floor 7. Work with Marketing on campaigns, standees, laptop wall paper, employee communication on emails, any other | 1. Boosts Employee Retention and Engagement 2. Enhanced Employee Advocacy 3. High Employee motivation and engagement - 5. Enhanced Employee performance and productivity -Employer branding aligns with company culture and values, resulting in higher employee motivation and better alignment between employees and company goals | 1. Improved Talent Acquisiion metrics -Offer Acceptance Rate, TAT to Hire, Applicant Quality Ratio, Cost-per-Hire Candidate net promoter score (NPS) 2. Enhanced Talent Retention & Engagement Metrics - Employee Retention/Turnover Rates, Employee Net Promoter Score (eNPS), Employee Referral Rate 4. Enhanced Glassdoor rating trend 5. Enhanced Social engagement - across platforms like LinkedIn, Glassdoor, Ambition Box and others. It includes likes, comments and others | i. VOW (Voice of Workforce) Survey drafted ii. VOW survey page created with questions based on GPTW survey iii. VOW Survey to be administered to curated business leaders by wk-1 May-26 iv. GPTW theme based VOW survey to be initiated from wk-2 June-26 month onwards
Building Organisation Culture of Compliance - Governance & Discipline
1 | Culture of Compliance | Ongoing | Q3-Jul-26 | 1. HR Policies Launch - Separation, Grievance Redressal, Under-Performance and Disciplinary Policy 2. Business Code of Conduct and Ethics document to be formulated 3. Employee Handbook to be revised to incorporate Central /State amended laws & regulations 4. POSH - ICC Committee member review. External Consultant to hold ICC member training and employee refreshers to meet statute requirements | 1. Risk Mitigation & Financial Security 2. Enhanced Reputation & Trust 3. Operational Efficiency 5. Employee Engagement & Morale 6. Long-term Business Sustainability: | 1. Improved Employee Retention 2. Consistent enforcement of policies & processes 3. Perceived Ethical Commitment from Leaderhsip at Organisation level 4. Speak-up cases with Management - number 5. Timely Issue Resolution 6. Reduction in Regulatory Fines 7. Healthy Brand Reputation | i. HR Policies - Separation, Grievance Redressal, Under- Performance & Disciplibary Policy drafted ii. PEP /PIP templates to be drafted iv. Employement letter - LOI, AL to be revised meeting the IT Acts, Central, State Statutes v. Meeting external POSH consultant for ICC member training
Note on C7: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Branding and creating visibility at company level
Note on C8: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Branding and creating visibility at company level
Note on C9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Branding and creating visibility at company level
Note on F18: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Constraint - Call record upload - size, time, data, storage issues
Note on C23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Constraint -No HR POC in Night Shift
Note on F23: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: TPA - Medi Assist, MDIndia, Paramount, Vidal Health, and Heritage Health Reply: Employee Assistance Program (EAP) providers include 1t01help, ComPsych, Lyra Health, Modern Health, Spring Health, and Workplace Options Reply: HR Process Digitization - XOXOday
Note on C27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Strategic shift from People to Process dependency. Business Continuity, Raises performance bar - pressure to upskill and innovate - Skill Obsolesence

## Medium Priority
HR Project Charter - 2026-27
| HR Projects | Frequency | Timelines for Institutionalization & Adoption | Action Plan | Business Impact | Success Measures | Status Update | Timelines Met /Deferred | Revised Timeline
SNO | Day 0 Employee Engagement - Productivity & Efficiency
1 | Staged Employee Assimilation Program - ASCENT Program (0-180 days) | One time Set-Up | Q4-Nov-26 | 1. Draft Employee Assimilation Plan for management review 2. Post Management approval, share program details with delivery 3. Process institutionalization with governance framework | 1. Higher Productivity - Structured, early integration helps new employees become productive faster 2. Enahanced employee retention and reduced turnover 3. Improved cultural alignment 4. Enhanced Employee experience and morale 5. Socialization and Mentorship | 1. Reduced New Hire Turnover - 0-6 months attrition % 2. Employee Engagement and Satisfaction - New Hire Satisfaction Score (NHSS) and Employee Net Promoter Score (eNPS) scores 3. ESAT Survey Score | 1. Draft version ot ASCENT Proccess created for review
2 | Staged Employee Experience Program - GROW Program (30-60-90 Days) | One Tme Set-up | Q4-Nov-26 | 1. Draft Employee Experience Plan for management review 2. Post Management approval, share program details with delivery 3. Process institutionalization with governance framework | 1. Role Clarity & identification of any gaps - alignment on performance expectations and goal setting 2. Relationship Building 3. Accelerated Productivity 4. Cultural & Team Integration | 1. Low infant mortality rate - 0-60 says attrition% 2. Goal and exipectation setting - KRA's signed off with manager 3. Productivity - accelerating time-to-productivity - % of goal met in first 90 days | 1. Draft version ot GROW Proccess created for review
SNO | HR Policies & Processes Standardisarion - Culture of Compliance and Governance
1 | Promotion Policy | Business & Compliance Requirements | Q2-May-26 | 1.Draft Policy for management review 2. Policy Awareness Session on floor for manager and employee sensitization 3. Employee acknoweldgement on HR Policies and Processes at onboarding stage 4. Incorporating State and Country Compliance requirements in the Employee Handbook (keeping it updated for any statte revisions) 5. Code of Conduct and Ethics Document creation 6. Employee Contracts - OL /LOI /AL - revision incorporating updated State and Central statutes | 1. Employee governance framework at an enterprise level 2. Legal Compliance and Risk Management 3. Operational Efficiency 4. Employee expectations and communication | 1. ESAT Survey Score 2. Employee Net Promoter Score (eNPS) score 3. Compliance and Risk - legal non-compliance case% 4. Productivity and Performance Metrics
2 | Employee Grievance Redressal Policy | [5 empty] | i. Policy drafted, shared with team for review and observations ii. Policy to be shared with Management for view and final accord
3 | Employee Hand Book
4 | Separation Policy | [5 empty] | i. Policy drafted, shared with team for review and observations ii. Policy to be shared with Management for view and final accord
5 | Performance Management Policy
6 | Employee Under- Performance and Disciplinary Policy | [5 empty] | i. Policy drafted, shared with team for review and observations ii. Policy to be shared with Management for view and final accord
7 | CSR Policy
8 | Travel Policy - Domestic & International
9 | L&D Policy - EYE (Enhance Your Education)
10 | Code of Conduct and Ethics | [5 empty] | i. CoC&E document drafted, shared with team for review and observations ii. Document to be sahred with Management for view and final accord
11 | Employment Contract Agreement documents | [5 empty] | i. AL document, shared with team for review and observations ii. AL letter template to be shared with Management for view and final accord
SNO | Strategic Workforce Planning
1 | EWS (Early Warning Signal) Program | Monthly | Q3-Sep-26 | 1. Draft EWS process note for management review 2. Post approval get EWS qustionnaire finalised, taking inputs from business 3. Monthly RAG Analysis sharing with business. 4. Implementing IDP plan for high performers and business critical resources | 1. Proactive retention management of High Performers 4. Enhanced employee retention and engagement 5. Enhanced performance and productivity | 1. No. of positions filled internally by IJP 2. Employee Net Promoter Score (eNPS) 4. Bottom Quartile Management (BQM) process % 5. Performance and Productivity metric changes
2 | Competency Framework Designing competencies and role mapping as per Career Framework | Process Guidelines | Q4-Dec-26 | 1. Draft Competency Framework for management review 2. Post management approval map the Roles with the competencies | 1. Identify skill and competency gaps more efficiently, customized training and professional development 2. Organizational culture alignment 3. Increased Organizational efficiency | 1. Streamlined Talent Acquisition process - early attrition% 2. Performance Management and Objectivity - ER cases% 3. Strategic Alignment and Data-ariven insights 4. Enhanced Training & Development - L&D programs%
Employee Collaboration - Productive and Innovative work environment
1 | Building CoP's (Communities of Practise) | Ongoing | Q1-Jan-27 | 1. Draft CoP process note document for management view 2. Define the function domain, community, and practice, and shortlist a core team. 3. Organize consistent meetings and use collaborative tools to foster, capture, and building knowledge repository | 1. High level of collaboration at an enterprise level 2. Accelerated Learning and Knowledge Management 3. Enhanced Innovation and Problem Solving 4. Knowledge Management & Innovation 5. Cross-Functional Collaboration - break down silos, sharing best practices and work together | 1. Employee Net Promoter Score (eNPS) - Employee statisfaction, engagement levela 2. Business Impact Metrics -Efficiency Gains, Innovation, strategic alignment to business goals 3. Knowledge and Learning Metrics 4. Process /Functional Innovation - Number of new ideas, products, or processes generated
2 | Building Process Training Academies | Ongoing | Q1-Jan-27 | 1. Draft Academy process note document for management view | 1. Cross pollination of SME knoweldge 2. Future readiness of talent/skill landscape - Bridging Skill Gaps 3. Process Optimization 4. Fostering a culture of Innovation 5. Internal process knowledge management and dissemination | 1. Employee Net Promoter Score (eNPS) - Employee statisfaction, engagement levela 2. Employee Turnover% 3. Internal Mobility/Promotion Rate%
Note on C32: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Branding and creating visibility at company level
Note on C33: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Branding and creating visibility at company level

## Low Priority
HR Project Charter - 2026-27
| HR Projects | Frequency | Timelines for Institutionalization & Adoption | Action Plan | Business Impact | Success Measures | Status Update | Timelines Met /Deferred | Revised Timeline
SNO | Operational Processes Streamlining & Standardisation
1 | Shared Services for HR, Finance | Process Timelines | Q1-Mar-27 | 1. Draft Process note of Shared Services requirement for management review. 2. Post approval discussing the Shared Services Structure with business leadres 2. Creation of shared services for HR and finance - India, Govt, UK /US) and HR | 1. Cost optimization - eliminating redundant roles and utilizing economies of scale 2. Improved resource utilization% 3. Process efficiency - standardized processes and best practices improve quality & execution 4. Enhanced compliance and consistency | 1. Operational excellence 2. Improved Service quality- high Employee Net Promoter Score (eNPS) and process adherence to SLA's 3. Identification of process redundancies 4. Cost Efficiency - Reduction in total cost of ownership (TCO) and cost per transaction
SNO | Employee Engagement - Increased Productivity & Innovation
1 | Employee Engagement Team (CFT team) - Employee Engagement, CSR, Health, Saftey & Envoirnment (HSE), Employee Resource Group (ERG) committees | Ongoing | Q3-Jul-26 | 1. Share draft version of the CFT employee engagement process note with management 2. Post Approval form employee CFT Committees to meet at a pre-defined frequency | 1. Co-opting delivery in Employee Engagement (Fun, CSR, HSE, DEIB and others)- collaborative decision making & employee involvement 2. Amplifying Employee voice, increasing empowerment and sense of ownership 3. Fostering Belonging and Community | 1. Lower Employee Turnover/Higher Retention Rates 2. Improved Employee Net Promoter Score (eNPS) 3. Improved Employee Engagement Survey Scores 4. Increased Diversity in Decision-Making | i. Employee Committes formed - CSR, HSE, ERG, EEG
2 | PHPO (PreHire PreOrientation) | Ongoing | Q3-Sep-26 | 1. Share draft version of PHPO process note with management 2. Post approval launch a pilot program | 1. Reduced "No-Shows" and Early Attrition 2. Stronger Cultural Alignment 2. Enhanced Employer Branding | 1. Attrition% in 0-60 days 2. Reduced Offer Drop-out/No-Show Rate 3. Offer Acceptance ratio
SNO | HR Internal Audit & Compliance Management
1 | HR Files – including mandatory documents Govt ID proofs, PAN Card, Education Certificates, Relieving /Experience letter from previous employers | Predefined Frequency | Ongoing | i. Predefine frequncy of Internal /External HR Audits ii. Noting Non-Conformities and working Action Plan to close the NC's | 1. Complete Documentation of employment records 2. Ensuring that HR Statutory requirements as laid by stattutes are met 3. Ensuring standardisation of documents as per ISO Standards 4. Creating readiness level for any external audit in future | 1. Internal & External Audits 2. Any notification from Statutory Compliance body
2 | HR Statutory Compliance – Organizational compliance on all statutory requirements including PF , UAN No. Generation, Gratuity & ESIC
3 | HR Policy Audit – Reviewing all active HR Policies and checking on any non-compliance